## Burn Down Chart
Project: | Minesweeper
Sprint # | 2
DATE:
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 1 | As a user, I want to be able to login and register from the main screen | Edit View | Ryan | 1 | bar: Day 1 to Day 10
| 2 | As a user, after logging in, I want the game board to be displayed | create view | Ryan | 1 | bar: Day 1 to Day 10
| 3 | As a user, I want the images to be scaled properly and arranged in logical order with a nice looking feel. | Edit view | Ryan | 2 | bar: Day 1 to Day 10
| 4 | As a user, I want the buttons state to update using the game logic to ensure the proper button are updated | Edit View and Controller | Ryan | 2 | bar: Day 1 to Day 10
| 5 | As a user, I want to be able to click on the button with the left mouse button and show a change when clicked. | Edit view and add Controller for button | Ryan | 3 | Day 7: 2; Day 8: 1
| 6 | As a user, I want the backend controllers to implement game logic and rules | Add Models for game | Ryan | 1 | bar: Day 8
1
|  |  |  | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 11 | 9.9 | 8.8 | 7.7 | 6.6 | 5.5 | 4.4 | 3.3 | 2.2 | 1.1 | 1.7764e-15
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 9 | 4 | 1 | 1

## Project Backlog
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that I can | Estimate (hours) | Assigned To | Sprint #
1 | Login Screen | app user | register and login | gain access to the game | 2 | Ryan | 1
2 | Login Screen | app user | provide server side validation | to ensure information is correct | 1 | Ryan | 1
3 | Database | app user | have my information stored in an sql database | login again when I return to the applocation | 2 | Ryan | 1
4 | Login Screen | app user | be forwarded to a success or fail page | know if my information was correct or not on registration | 1 | Ryan | 1
5 | Login Form | app user | fill out a login form | login | 2 | Ryan | 1
6 | controller | app user | have the login form connected to the database | ensure authentication | 1 | Ryan | 1
7 | view | app user | be forwarded to a success or fail page | to ensure information is correct on login | 1 | Ryan | 1
8 | view | app user | login from the main screen | easily navigate application | 1 | Ryan | 2
9 | game view | app user | login | have the game board displayed for me to play | 1 | Ryan | 2
10 | game view | app user | have the images displayed and scaled properly | have an aestecical experience | 2 | Ryan | 2
11 | controller & game view | app user | have the buttons state to update using the game logic | ensure the proper buttons are being updated | 2 | Ryan | 2
12 | controller & game view | app user | be able to left click on a button | show the button status change visually | 3 | Ryan | 2
13 | controller | app user | have the backend controllers to implement the game logic | eventually play the game | 1 | Ryan | 2

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time