## Burn Down Chart
Project: | Minesweeper
Sprint # | 1
DATE:
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 1 | As a user, I want to be able to fill out a registration form with my First Name, Last Name, Sex, Age, State, Email, Username, and Password. | build controller | Ryan | 2 | Day 6: 2
|  | As a user, I want the registration form to perform server-side form validation to ensure my information is correct. | build model | Ryan | 1 | bar: Day 1 to Day 10
|  | As a user, I want my information to be saved in a SQL Server relational database when I submit the registration form | Build database | Ryan | 2 | bar: Day 1 to Day 10
|  | As a user, I want to be forwarded to a success or error page after submitting the registration form. | Add Views | Ryan | 1 | bar: Day 1 to Day 10
|  | As a user, I want to be able to fill out a login form with my Username and Password. | Add more views | Ryan | 2 | Day 7: 2
|  | As a user, I want the login form to use the SQL Server database for authentication. | Add Security Model | Ryan | 1 | bar: Day 8
|  | As a user, I want to be forwarded to a success or error page after submitting the login form. | Connect Security Model to login Controller | Ryan | 1 | bar: Day 8
|  |  | Task 8 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Task 9 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Task 10 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 2 | 0 | 0

## Project Backlog
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that I can | Estimate (hours) | Assigned To | Sprint #
1 | Login Screen | app user | register and login | gain access to the game | 8 | Shad | 1
2 | Login Screen | app user | choose the difficulty | start a new game. | 12 | Shad | 1
3 | User manager | admin | see a list of user accounts | print a report of current accounts |  |  | 2

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time